Basic OpenAgile Process Rules

_____	There is a single results-oriented Goal for the endeavour (the work being done)

_____	There are at least five (5) Cycles from start to finish in an endeavour to reach a Goal

_____	The intention of every Cycle is to deliver tangible value and progress towards the Goal

_____	Every Cycle is the same length

_____	There are no breaks between Cycles

_____	Every Cycle has at least five (5) Work Periods

_____	Every Cycle has the same number of Work Periods

_____	Every Work Period is the same duration

_____	There is an Engagement Meeting at the start of the first Work Period of every Cycle

_____	The Engagement Meeting meeting is time-boxed to the same duration every Cycle

_____	The time-box of the Engagement Meeting is set by the Team

_____	The Engagement Meeting includes Reflection on the previous Cycle

_____	The Engagement Meeting includes Learning from the previous Cycle

_____	The Engagement Meeting includes Planning for the next Cycle

_____	The Team does no work during the Engagement Meeting

_____	The Engagement Meeting results in a Cycle Plan

_____	The Cycle Plan includes Value Drivers and associated Tasks

_____	The Cycle Plan is owned by the Team

_____	The Cycle Plan is visible and accessible to all Stakeholders

_____	The Tasks in the Cycle Plan describe Repetitive Activities, Calendar Events, Obstacles, Quality Problems, and New Artifacts

_____	There is a Progress Meeting at the start of every Work Period in a Cycle except the first

_____	The Progress Meeting is time-boxed to the same duration every Work Period

_____	The Progress Meeting is short in proportion to the duration of a Work Period

_____	The Progress Meeting includes Reflection on Tasks done in the previous Work Period

_____	The Progress Meeting includes Learning about changes to the Cycle Plan

_____	The Progress Meeting includes Planning Tasks to be completed in the current Work Period

_____	The Team Members are people doing Tasks in the Cycle Plan

_____	The Team includes the Team Member(s) doing Growth Facilitation

_____	The Team includes the Team Member(s) doing Process Facilitation

_____	The Team does not include any other people (eg a manager who doesn't do Tasks)

The List of Value Drivers

_____	All Value Drivers in the List of Value Drivers are related to the Goal

_____	Value Drivers are prioritized or ordered by expected Value

_____	Value Drivers are pieces of the end results of the Goal (not intermediate results)

_____	The List of Value Drivers is prepared to ensure it is ready for every Engagement Meeting

_____	Any stakeholder of the Goal can suggest a new Value Driver (including Team Members)

_____	The List of Value Drivers is easily visible and accessible to every stakeholder

OpenAgile Team Member Role

_____	I use OpenAgile to create an environment in which people are free to express their true nature and capacities to contribute to the betterment of their organization

_____	I practice Truthfulness with my fellow Team Members about the status of my work and its workmanship
_____	I use Consultative Decision-Making with my fellow Team Members about all significant choices and actions

_____	I apply Systematic Learning with my fellow Team Members to all aspects of my work

_____	I explore Organic Growth with my fellow Team Members in all aspects of my work

_____	I am fully committed, personally and professionally, to the Goal of my Team

_____	I actively seek to help my fellow Team Members

_____	I commit myself to doing whatever it takes to fully execute each and every Cycle Plan

_____	I volunteer for a new Task from the Cycle Plan as soon as I complete a Task

_____	I am willing to learn any skill needed to help my Team

_____	I take direction for the Goal of the Team from Team Member(s) doing Growth Facilitation

_____	I attend every Engagement Meeting in-person

_____	I attend every Progress Meeting in-person

_____	The majority of time on Tasks is in the same physical work space as all Team Members

_____	I never tell any other individual Team Member which Task to work on

_____	My official title is “Team Member”

The Process Facilitation Path of Service

_____	I practice Truthfulness about the condition of the OpenAgile process and Foundations in my Team

_____	I use Consultative Decision-Making with my fellow Team Members about advancing the OpenAgile process and Foundations

_____	I apply Systematic Learning with my fellow Team Members about advancing the OpenAgile process and Foundations

_____	I explore Organic Growth with my fellow Team Members about advancing the OpenAgile process and Foundations

_____	I believe that OpenAgile will help my Team improve

_____	I work with only one OpenAgile Team

_____	I know OpenAgile well and can explain it both quickly and in detail to others

_____	I facilitate time-boxing the Engagement Meetings

_____	I facilitate the techniques used in the Engagement Meetings

_____	I facilitate time-boxing the Progress Meetings

_____	I facilitate the techniques used in the Progress Meetings

_____	I facilitate time-boxing the Cycle

_____	I am allowed to communicate directly with any stakeholder of the Team

_____	I facilitate the creation and improvement of Team Standards

_____	I have the bandwidth and capacity to respond within minutes to my Team's questions

_____	I measure the Team's Commitment Velocity

_____	I never tell any individual Team Member which Task to work on

_____	No member of my Team reports to me

The Growth Facilitation Path of Service

_____	I practice Truthfulness about progress towards the Goal and capacity of my Team to execute on Value Drivers

_____	I use Consultative Decision-Making with my fellow Team Members about advancing towards the Goal and developing Team capacity

_____	I apply Systematic Learning with my fellow Team Members about advancing towards the Goal and developing Team capacity

_____	I explore Organic Growth with my fellow Team Members about advancing towards the Goal and developing Team capacity

_____	I believe that OpenAgile will help my Team improve

_____	I work with only one OpenAgile Team

_____	I know OpenAgile well and can explain it both quickly and in detail to others

_____	I create and maintain the list of Value Drivers

_____	I empower Team Members to accomplish Tasks in the Cycle Plan

_____	I facilitate the use of a Skills Matrix to develop Team capacity

_____	I measure progress towards the accomplishment of the Goal

_____	I am allowed to communicate directly with any stakeholder of the Team

_____	I have the bandwidth and capacity to respond within minutes to my Team's questions

_____ I always let my Team freely decide how many Value Drivers to work on in a Cycle

_____	I never tell any individual Team Member which Task to work on

_____	No member of my Team reports to me