Basic Process Facilitation Methods
The Engagement Meeting

# Background
The Engagement Meeting is held at the beginning of each Cycle. The beginning of the Engagement Meeting marks the beginning of the Cycle's overall timebox. Process Facilitation for the Engagement Meeting ensures that the following attributes of the Engagement Meeting are met:
- Purpose: to take some time for systematic and practical learning
- Attendees: all individuals doing work to deliver Value Drivers (the “team” or the “community”)
- Agenda: “Reflect”, “Learn” and “Plan”
- Outcome: a “Cycle Plan”
The following three methods of facilitating the Engagement Meeting can all be used by teams new to OpenAgile. Each has a different emphasis and so some notes are provided on selecting a method.
# Method 1
Name: Highlights – Learning – Improvements
Time Required: 30 minutes to 180 minutes
Materials Required: whiteboard and three strong colors of whiteboard markers (e.g. black, red and blue)
## Process
The Team Member serving to do Process Facilitation prepares a whiteboard or similar highly-visible writing area. This Team Member asks the following questions of the team and records the answers on the whiteboard using a different color marker for each question. The team is given a little less than one third of the overall time for each question. The remainder of the time is for the team to do any other planning they wish for the Cycle.
Question One: Share some highlights of the Cycle just completed. What was notable?
Question Two: What did you learn?
Question Three: Based on the highlights and what we learned, what can we improve this Cycle?
The person facilitating the process must faithfully write all responses without judgement on the whiteboard.
After Question Three, the team has an open discussion to choose Value Drivers and create Tasks for the Cycle. Facilitation should focus on connecting the results of Question Three to the Cycle Plan that is created.
# Method 2
Name: Temperature – Starfish Chart – Strategy/Action
Time Required: 30 minutes to 90 minutes
Materials Required: thick flip chart markers (each team member gets a different color), long scroll of wide butcher paper, tape or pins to fasten the paper to a wall, flip chart or whiteboard and appropriate marker, 4x6 note cards and medium tip black Sharpies (one for each team member)
Process
The Team Member serving to do Process Facilitation prepares a stretch of wall by putting up a long scroll of butcher paper. Ideally it is about 10 feet long and positioned so that people standing at the wall can easily write on the paper.
Once all Team Members are in the space, the person facilitating welcomes people and explains the Engagement Meeting exercise by saying something like:
“Today we are going to do a temperature timeline to reflect on our past Cycle. Then we will use a starfish chart to identify things we have learned. Finally we will use the strategy/action technique to plan our Cycle.”
The person facilitating then hands out a colored flip chart marker to each team member while introducing the temperature timeline by saying:
“The temperature chart shows us how intense our emotions were during the last cycle. Each person will draw a horizontal line along the paper on the wall. The left end of the paper is the start of the Cycle, the right end is the end of the Cycle. Your line
# Method 3
Name: Triple Bottom Line – Reviewing Value – Core Types
Time Required: 60 minutes to 120 minutes
# coaching for Engagement Meeting Process Facilitation
If you are coaching someone to use these methods, you will demonstrate each method once by facilitating the Engagement Meeting of a team. Then you and the person you are coaching co-facilitate each method once. Finally, you observe the other person facilitating each method once. You are looking for the following skills:
1. Time management. Moving the team through each part of the method in a timely manner so that the overall Engagement Meeting timebox is maintained.
2. Logistics. The right people are invited and attend. The space and materials are prepared.
3. Encouragement. Helping the other Team Members understand and engage with the various parts of each method.
4. Connection. Facilitating the smooth flow of one part of each method to the next part.
5. Light touch. Imposing the least amount of self into the process.
You are also looking for signs that the person facilitating has a clear understanding of the foundations of OpenAgile (Truthfulness, Consultative Decision-Making and Systematic Learning).