## Sheet1
				Team Formed
OpenAgile Assessment Worksheet*					Pre-Agile	Goal State	Cycle 0	Cycle 1	Cycle 2	Cycle 3	Cycle 4	Cycle 5	Cycle 6	Cycle 7	Cycle 8	Cycle 9	Cycle 10
				0	0	0	0	0	0	0	0	0	0	0	0	0
		Formed Rules (Level 1)
			Team agrees to learn and practice Truthfulness
			Team agrees to learn and practice Consultative Decision-Making
			Team goes through a process of Reflection, Learning, Planning and Action in short Cycles
			Team is aware of the broad goal
			Prospective Team membership determined
			Team agrees to work towards Launched Rules

		Launched Rules (Level 2)
			Work Cycle is a consistent length
			Team is committed to a single clearly-articulated and well-defined project or operational Goal
			Team has Cycle Engagement meetings
			Team has Progress meetings
			Team members are all at “Readiness” level **
			Team agrees to work towards Stable Rules

		Stable Rules (Level 3)
			Ten Cycles completed (at least)
			Key performance metric for Goal is defined and measured
			All Team members are that the “Team Member” level **
			One Team member is at the “Process Facilitation” level **
			One Team member is at the “Growth Facilitation” level **
			For “projects”, Work Cycle is at most 1/5th duration of overall effort
			Cycle Engagement Meeting is timeboxed
			Engagement Meeting includes Reflection
			Engagement Meeting includes Learning (focused on Value Drivers)
			Engagement Meeting includes Planning (choosing Value Drivers to work on)
			The whole Team commits to the Cycle Plan
			Team holds Progress Meeting at regular intervals at least four times per Cycle
			Non-leveled OpenAgile rules adoption level at 50% for at least 3 Cycles in a row
			Team agrees to work towards Performing Rules

		Performing Rules (Level 4)
			Twenty Cycles completed (at least)
			Key performance metric for Goal is measured and increasing for 70% of trailing Cycles
			All Value Drivers are clearly related to the Goal
			Progress Meeting includes Reflection
			Progress Meeting includes Learning
			Progress Meeting includes Planning
			Team Standards defined
			Cycle Engagement Meeting Learning includes Team Standards
			Team Cycle Plan is visible in a Team Room
			Team Cycle Plan is updated every Progress Meeting
			All Consultative Decision-Making takes place in Team Room
			Non-leveled OpenAgile rules adoption level at 70% for at least 5 Cycles in a row
			Team agrees to work towards Sustainable Rules

		Sustainable Rules (Level 5)
			Thirty Cycles completed (at least)
			Key performance metric for Goal is measured and increasing for 90% of trailing Cycles
			Second Team member is at the “Process Facilitation” level **
			Second Team member is at the “Growth Facilitation” level **
			One Team member is at the “Mentor” level **
			Non-leveled OpenAgile rules adoption level at 90% for at least 10 Cycles in a row
			OpenAgile Performance Metrics measured and trending upwards
			Limit Individual Work-In-Progress (WIP)
			Limit Team Work-In-Progress (WIP) with either Commitment Velocity or Per-Stage WIP Limits (Kanban)

		Innovating (Level 6)
			Controlled experiments to measure the effect of changes in the OpenAgile rules
			Contributing results of experiments to the OpenAgile community
			The Foundations of OpenAgile are upheld

		Non-Leveled OpenAgile Rules to Implement As Soon As Possible:
			Cycle Engagement Meeting results in a Cycle Plan consisting of many Tasks
			Team tracks five types of work as tasks:
				Calendar Events
				Repetitive Activities
				Quality Problems
				Obstacles
				New Artifacts
			Team writes SMART Value Drivers
			Team prioritizes Value Drivers
			Team seeks Guidance (advice, help, information, accompaniment)
			Team Members Volunteer for Tasks
			Team uses Consultative Method to make all decisions
			Process Facilitator tracking and removing Obstacles
			Process Facilitator helping Team with OpenAgile Rules
			No “Break” Between Cycles
			Sustainable Pace – Timebox Effort, Not Just Schedule
			Tasks Added/Updated/Removed in the Cycle Plan by Team
			Cycle Burndown Chart Based on number of Tasks remaining
			Commitment Velocity Calculated (from Cycle Burndown)
			Growth Facilitator helps Team prioritize Value Drivers
			Growth Facilitator helps Team build capacity
			Team Room with All Needed Equipment and Supplies
			Team of Volunteers – Self-Selecting

		OpenAgile Performance Metrics:
			Customer Satisfaction: Communication
			Customer Satisfaction: Progress
			Customer Satisfaction: Availability
			Customer Satisfaction: Organization
			Customer Satisfaction: Quality
			Team Satisfaction: Communication
			Team Satisfaction: Progress
			Team Satisfaction: Availability
			Team Satisfaction: Organization
			Team Satisfaction: Quality
			Management Satisfaction: Communication
			Management Satisfaction: Progress
			Management Satisfaction: Availability
			Management Satisfaction: Organization
			Management Satisfaction: Quality

		* Rules are cumulative for the Team Levels – all rules in a given level and all lower levels must be “yes” / Or “4/4” for the team to be considered to be at that level
		** Individual levels do not require actual certification unless the Team wishes to be certified